## Slide 1: Airport Carpark: Budget Performance
CONSTRUCTION OPERATIONS ANALYTICS
Budget vs. final cost across work packages
52
work packages compared
−$51,479
net variance (favorable)
2.66%
below combined budget
Notes: Overview: 52 comparable packages finished $51,479 (2.66%) under their combined budget. The rest of the deck explains why that headline needs care.

## Slide 2: 52 of 63 packages could be compared
63
Work packages identified
59
Have a budget value
54
Have a final cost
52
Have both: fully comparable
11
packages have incomplete financials
7 budget, no final cost
2 final cost, no budget
2 missing both
Missing values were kept as missing, never assumed to be zero.
Notes: Data was imported to BigQuery, cleaned in SQL, and validated. Only packages with both budget and final cost are in the like-for-like comparison.

## Slide 3: Net result is favorable, but split 26 / 26
Chart: Comparable packages (52)
| Combined budget | Combined final cost
Total | 1933569.37 | 1882090
26
packages over budget
26
packages under budget
The $51,479 saving masks large package-level swings and does not prove the project finished under budget.
Notes: Combined budget $1,933,569.37 vs final $1,882,090.00. Variance = final minus budget. Half the packages overran.

## Slide 4: Five packages drive the largest overruns
Chart: Overrun over budget ($)
| Sweep & Prime / Primer Seal | QMS Sand | Project Supervision | Place & Compact Gravel | Stockpile to Fill
Overrun | 36308.9 | 40199.32 | 44739.9 | 51212.68 | 69889.56
$342,041
combined overrun of the ten largest packages
Stockpile to Fill alone ran $69,890 over: budget $94,981 vs. final $164,871.
These show where costs differed, not why.
Notes: Top five: Stockpile to Fill, Place & Compact Gravel, Project Supervision, QMS Sand, Sweep & Prime. Causes not established by the data.

## Slide 5: Three issues limit confidence in the results
3,771%
Percentage outlier
Cement Powder (stabilising): budget $332, final $12,852. Huge percentage, but only $12,520 in dollars.
11
Incomplete records
Packages lack budget, final cost, or both. Results cover only the 52 complete ones.
$1,400
Unreconciled gap
Survey – Construction: $27,030 on the WBS sheet vs. $28,430.20 in actual transactions.
Review dollar and percentage variance together; totals are not a fully reconciled project cost.
Notes: Small budgets create huge percentages; large packages create large dollar impact. Missing values must be investigated before closeout.

## Slide 6: Recommended next steps
1
Investigate the five largest overruns
Check records, quantities, rates and approved variations
2
Review percentage outliers separately
Confirm small budgets and unit rates are recorded correctly
3
Resolve the 11 incomplete records
Pending, omitted or not performed? Never assume zero
4
Reconcile the $1,400.20 Survey difference
Match WBS totals to actual cost transactions
5
Make validation repeatable
Standard checks and exception reporting for future reviews
Notes: Priority: investigate largest variances, close data gaps, reconcile the Survey discrepancy.