Construction Operations Analytics

Airport Carpark Project — Budget Performance Analysis

Project type: Construction cost and budget analysis
Tools: Excel, Google BigQuery, SQL
Dataset: Project Portfolio Dataset — Airport Carpark

| 52 PACKAGES COMPARED | −$51,479 NET VARIANCE | 2.66% BELOW COMBINED BUDGET |
| --- | --- | --- |

# 1. Executive Summary

This project examines budget performance across work packages within an Airport Carpark construction project. Using Excel and SQL in Google BigQuery, the analysis focused on validating the source data, standardizing financial fields, assessing budget-to-final-cost variance, and identifying work packages that warrant further investigation.

The source data contained 63 identifiable work packages. Of these, 52 had both budget and final-cost values available, allowing for a like-for-like comparison.

Across those 52 work packages, the combined budget was $1,933,569.37, compared with a combined final cost of $1,882,090.00. This produced a net favorable variance of $51,479.37, or approximately 2.66% below budget.

However, the net result masks substantial differences at the work-package level. Twenty-six packages exceeded their budgets, while 26 finished below budget. Additionally, 11 packages had incomplete financial information, limiting the scope of the comparison.

The findings highlight the importance of evaluating individual cost variances alongside overall project totals. The analysis also identified a financial discrepancy requiring further reconciliation before the project’s costs can be considered fully validated.

# 2. Business Objective

The objective was to assess how actual or final costs compared with budgeted amounts, identify the work packages contributing most to cost overruns, and evaluate whether the available data was sufficiently complete and consistent to support reliable reporting.

The analysis was designed to answer four questions:

- How did final costs compare with budget across work packages with complete financial data?

- Which work packages had the largest cost overruns?

- Which records had missing or incomplete financial information?

- What additional validation is needed before stakeholders rely on the results?

# 3. Data Preparation and Validation

The source workbook was imported into BigQuery for structured analysis. SQL was used to inspect the data, identify work-package records, standardize financial fields, and validate the resulting analytical table.

Key preparation steps included:

- Identifying valid work-package records and excluding blank or non-package rows from the analytical table.

- Checking work-package identifiers for duplicates.

- Converting budget and final-cost fields from text to numeric values.

- Removing thousands separators and treating dash placeholders as missing values.

- Validating the cleaned table and assessing financial-data completeness.

- Comparing available totals with the source workbook’s reported figures.

The cleaned analytical table contained 63 work packages. Budget values were available for 59 packages, and final costs were available for 54. Only 52 contained both values needed for a direct budget comparison.

Missing values were retained as missing rather than assumed to be zero. This prevents incomplete records from distorting the analysis.

# 4. Key Findings

## Finding 1 — Net cost performance was favorable across comparable work packages

| Metric | Result |
| --- | --- |
| Work packages compared | 52 |
| Combined budget | $1,933,569.37 |
| Combined final cost | $1,882,090.00 |
| Net variance | −$51,479.37 |
| Net variance as a percentage of budget | −2.66% |
| Packages over budget | 26 |
| Packages under budget | 26 |

The comparable work packages finished approximately 2.66% below their combined budget.

However, the net variance should not be interpreted as proof that the overall project was completed under budget. The result covers only packages with both financial values available, and the analysis does not establish why individual variances occurred.

## Finding 2 — Significant overruns were concentrated in specific work packages

The largest positive dollar variances identified several packages that should be prioritized for review.

| Work package | Budget | Final cost | Overrun |
| --- | --- | --- | --- |
| Stockpile to Fill | $94,981.44 | $164,871.00 | $69,889.56 |
| Place & Compact Gravel | $40,636.32 | $91,849.00 | $51,212.68 |
| Project Supervision | $38,411.10 | $83,151.00 | $44,739.90 |
| QMS Sand | $10,432.68 | $50,632.00 | $40,199.32 |
| Sweep & Prime / Primer Seal | $69,649.10 | $105,958.00 | $36,308.90 |

These five packages represent substantial cost differences relative to their respective budgets. The ten largest dollar overruns totaled approximately $342,040.66, making them useful starting points for a more detailed cost review.

The figures identify where the differences occurred; they do not, by themselves, explain the underlying causes.

## Finding 3 — Percentage overruns revealed additional areas of concern

Ranking packages by percentage variance produced a different perspective from ranking them by dollar impact.

For example, Cement Powder (stabilising) had a budget of $332 and a final cost of $12,852, a variance of $12,520 or approximately 3,771%.

Although the percentage variance is exceptionally high, its dollar impact is smaller than that of Stockpile to Fill or Place & Compact Gravel.

This demonstrates why percentage and dollar variance should be reviewed together. A small budget can produce a very large percentage overrun, while a larger package can have a greater financial impact despite a lower percentage variance.

## Finding 4 — Incomplete financial records limit the conclusions

Eleven work packages did not have both budget and final-cost values available.

The records included:

- Seven packages with a budget but no final cost.

- Two packages with a final cost but no budget.

- Two packages missing both values.

These gaps prevent a complete work-package-level comparison. Missing values should be investigated before the results are used for final project closeout or financial reporting.

# 5. Recommendations

Based on the findings, the following actions are recommended:

1. Investigate the highest-dollar overruns.
Begin with Stockpile to Fill, Place & Compact Gravel, Project Supervision, QMS Sand, and Sweep & Prime / Primer Seal. Review supporting cost records, quantities, rates, scope changes, and any approved variations to determine the reasons for the differences.

2. Review percentage outliers separately.
Investigate work packages with unusually high percentage variances, especially where the original budget was small. Confirm that the budget, quantity, unit rate, and final cost are comparable and correctly recorded.

3. Resolve missing financial values.
Confirm whether the 11 incomplete records represent pending costs, omitted values, work not performed, or another reporting issue. Do not treat missing amounts as zero without supporting evidence.

4. Reconcile work-package totals against supporting cost records.
A discrepancy was identified for Survey - Construction (WBS 11): the Portfolio WBS sheet lists a final cost of $27,030, while the reported sum of transactions in the Actual Costs sheet is $28,430.20. The $1,400.20 difference requires investigation before the figures can be considered fully reconciled.

5. Establish a repeatable reporting process.
Maintain a consistent workflow for data validation, financial-field conversion, variance calculations, exception reporting, and reconciliation. This would make future cost reviews more repeatable and easier to audit.

# 6. Methodology and Limitations

Cost variance was calculated as:

Cost variance = Final cost − Budget

Variance percentage = (Final cost − Budget) ÷ Budget × 100

A positive variance indicates that final cost exceeded budget; a negative variance indicates that final cost was below budget.

The main comparison included only work packages with both budget and final-cost values present. Percentage calculations excluded records with zero or missing budgets.

The results are subject to several limitations:

- Financial values were incomplete for 11 of the 63 identified work packages.

- A discrepancy remains between the Survey - Construction final cost and the reported supporting transactions.

- Cost variances indicate the size and direction of differences but do not establish their causes.

- A below-budget result does not necessarily represent realized savings; scope, quantity, timing, and data completeness must also be considered.

- The comparable-work-package totals should not be treated as a fully reconciled final project cost.

# 7. Conclusion

The comparable work packages finished $51,479.37 below their combined budgets, but this favorable net result coexisted with 26 over-budget packages and significant individual overruns. The findings show why aggregate totals alone are insufficient for understanding construction cost performance.

The next priority is to investigate the largest cost variances, resolve incomplete financial records, and reconcile the discrepancy between the Portfolio WBS and Actual Costs sheets. Completing those checks would strengthen confidence in the analysis and provide a more reliable basis for operational and financial decisions.

Project deliverables: SQL data validation, data profiling, cleaning, cleaned-table validation, budget variance analysis, and findings suitable for a management report or dashboard.

Dataset source: Project Portfolio Dataset, Figshare.
https://figshare.com/articles/dataset/Project_Portfolio_Dataset/12998822